CHA-39 — 2-Day Execution Plan

AI/ML + RBAC/IAM — Chaitanya Thakar

Build: 2 days  |  Integration & test: 1–1.5 days. Assumes ~7 focused hours/build day — rescale blocks proportionally if your actual hours differ.

# 1. Verdict on the Original Checklist

The core ML design (15-minute sliding-window features, Isolation Forest, explainability, frozen-baseline training, DB-polling watcher) is sound and already built and tested — it carries over directly. Three items in the original checklist do not fit a 2-day budget and are cut or demoted below: Hugging Face Spaces deployment (free tier sleeps after 48h of inactivity and cannot be configured otherwise — real risk of a dead endpoint exactly when judges try it), a dedicated FastAPI /predict service (redundant with the DB-polling watcher already built, unless Jiya specifically wants direct HTTP forwarding instead), and the NSL-KDD benchmark script (demoted from a core deliverable to a hard-capped, cut-if-behind stretch item for Slide 6 only).

# 2. Day 1 — Core Build

| Time | Task | Est. | Priority |
| --- | --- | --- | --- |
| 0:00–0:30 | Send the 4 cross-team contract messages (Het / Jiya / Riddhi / Maharshi — exact text in Section 3). Blocking — do this before anything else. | 30 min | Must-do |
| 0:30–2:30 | Adapt anomaly_detection.py + train_and_save_model.py to the confirmed (or interim) schema; regenerate the baseline model. | 2 hr | Must-do |
| 2:30–4:00 | Adapt live_watcher.py to poll the real table and write to the real alerts schema (add severity, map column names). | 1.5 hr | Must-do |
| 4:00–5:00 | Write the RBAC matrix as a Casbin policy (rbac_model.conf + policy.csv) from the matrix already in cha39_rbac_iam_ml_plan.docx; write the JWT claim schema for Jiya/Maharshi. | 1 hr | Must-do |
| 5:00–5:45 | Server telemetry threshold check (CPU > 90% or Temp > 75°C for 3 consecutive cycles → PREDICTIVE_HARDWARE_ALERT). | 45 min | Cut-if-behind |
| 5:45–7:00 | Buffer. Smoke-test whatever pieces exist so far. | 1.25 hr | Must-do |

# 3. Day 2 — Integration & Polish

| Time | Task | Est. | Priority |
| --- | --- | --- | --- |
| 0:00–2:00 | Full pipeline integration test against the real (or staging) Postgres — confirm the write/read cycle end to end. | 2 hr | Must-do |
| 2:00–3:00 | Fix whatever breaks in integration. This slot is reserved, not optional — something will break. | 1 hr | Must-do |
| 3:00–3:30 | Confirm Jiya's /alerts endpoint reads correctly; confirm Riddhi's frontend renders one real flagged event. | 30 min | Must-do |
| 3:30–5:00 | NSL-KDD benchmark script (Precision/Recall/F1/ROC-AUC + one plot) for the Slide 6 reference — hard cap, stop at 5:00 regardless of progress. | 1.5 hr max | Cut-if-behind |
| 5:00–6:00 | Rehearse the 3 judge-defense answers out loud (Section 4) until you can say them without reading. | 1 hr | Must-do |
| 6:00–7:00 | Buffer. | 1 hr | Must-do |

# 4. Testing (1–1.5 Days)

| Time | Task | Est. | Priority |
| --- | --- | --- | --- |
| Day 3, 0:00–1:30 | Re-seed clean demo data; retune the contamination parameter against real/near-real traffic so alerts aren't noisy. | 1.5 hr | Must-do |
| Day 3, 1:30–3:30 | Full team run-through: login → RBAC gate → injected anomaly → alert → dashboard, start to finish. | 2 hr | Must-do |
| Day 3, 3:30–4:30 | Edge cases: no anomalies present, alerts table briefly unreachable, watcher restart behaviour. | 1 hr | Must-do |
| Day 3, 4:30–6:00 | Full timed dry-run of the demo script/pitch. | 1.5 hr | Must-do |
| Day 4 (half day) | Final fixes from Day 3's dry-run; one more full rehearsal; freeze the demo dataset. | 2–3 hr | Must-do |

# 5. Cross-Team Contracts — Send These First

- Het (Database): Confirm which table feeds Isolation Forest — monitoring_metrics (server telemetry) or a dedicated auth/access-event table. His current audit_logs is described as admin/data-change records, not raw per-login telemetry; if auth events are the source, a new table is needed. Also confirm the alerts table matches: id, user_id, severity, anomaly_score, is_anomaly, top_reason, created_at.

- Jiya (Backend): Confirm DB-polling (watcher writes to alerts, Go reads from it) versus direct HTTP forwarding to a prediction endpoint. Default to DB-polling — it's already built; only build the HTTP path if she specifically needs it.

- Riddhi (Frontend): Send the exact JSON shape her Anomaly Inspector Modal should expect: user_id, window, anomaly_score, is_anomaly, top_reason, severity.

- Maharshi (Architect): Confirm the 4 role strings are final: viewer, operator, admin, super-admin — these are what the Casbin policy and JWT claim are built against.

# 6. Explicitly Cut for This Timeline

- Hugging Face Spaces deployment — skip entirely. Confirmed free-tier Spaces sleep after 48 hours of inactivity with no way to disable this on the free plan; not worth the setup time or the demo-day risk.

- Dedicated FastAPI /predict service — skip unless Jiya explicitly asks for direct HTTP forwarding. The DB-polling watcher already covers this.

- Full NSL-KDD benchmark suite — demoted to a 1.5-hour hard-capped stretch item on Day 2. If it doesn't finish in that window, cut it and mention the algorithm choice is validated in principle, not with a live number.

- Server telemetry threshold alerting — cheap, but genuinely optional; first thing to drop on Day 1 if the core pipeline runs long.

# 7. Judge Defense — Rehearse These Out Loud

- Why Isolation Forest over LSTM/Autoencoders? Unsupervised, tree-based, near-linear training time, sub-millisecond inference — no need for millions of labelled attack records or GPU infrastructure to get real-time explainable flags.

- How do you prevent model poisoning? No blind online retraining on live traffic. The model trains on a frozen, verified baseline snapshot; updates only happen via scheduled retraining on audited, human-reviewed logs.

- How does this fit Zero Trust? Traditional auth only checks identity at login. This adds continuous behavioural verification during the session — anomalous activity can flag or help revoke a session's trust, not just the initial login.